## Slide 1: CREWS Project Development Procedures
CREWS Steering Committee, 12 September 2016, WMO, Geneva, Switzerland
CREWS/SC.1/Infdoc.2

## Slide 2: CREWS Programming Principles
Country ownership
Targeting life saving needs
Leveraging resources
Integrated and inclusive programming
National institutions engaged from early stages of programming and leading on implementation
Addressing countries and programmes without capacity and system to issue timely warnings
Potential to increase investment levels and provide wider economic, environmental, social including gender, co-benefits
CREWS work plan guides projects by Implementing Partners, based consultations with countries and partners and joint identification of needs and priorities
Steering Committee Meeting 12 September 2016 WMO, Geneva, Switzerland

## Slide 3: Operational Roles and Responsibilities
Steering Committee
ensures consistent operations
Implementing Partners
consults with recipient countries, and all stakeholders
Secretariat
Trustee
receives and reviews Project Proposals
keeps Trustee informed to carry out its responsibilities
prepares operational guidelines (eligibility, process and format for Projects)
collaborates with the Secretariat with information necessary to carry out its responsibilities
provides Steering Committee with regular reports on the financial status
uses CREWS funds in accordance with its own policies and procedures
approves operational guidelines (eligibility, process and a common format for Projects)
reviews and approves Projects
assists all stakeholders in the design of the Projects and implementation
maps status of early warning systems in SIDS and LDCs

## Slide 4: Project Development Process
1. Mapping
Prioritized countries based on mapping of LDCs and SIDS capacities and needs and the potential for leveraging additional resources.
2. Investment Plan
Identifies funding flows, project countries and programmatic areas for the development of CREWS projects
3. Project development
Identified priorities, alignment with relevant ongoing initiatives and Regional and Global Support projects.
4. Project submission
Lead Implementing Partner submits project to Steering Committee through the CREWS secretariat for approval and allocation of funds.
Guided by CREWS Programming Framework
Identification of lead Implementation Partner
Multi-stakeholder consultations in country or region.
Quality control of projects by CREWS secretariat.
Integrated Programming
Steering Committee Meeting 12 September 2016 WMO, Geneva, Switzerland

## Slide 5: Integrated Programming
Joint and continuous mapping of priority countries and needs.
Guided by CREWS Programming Framework
Identified Project countries
Global coherence and advocacy support
Joint programming and consultations in project countries
Regional support
Country project
Regional support project
Country project
Global project
Projects led by an
Implementing Partner
Joint Programming Steps
Steering Committee Meeting 12 September 2016 WMO, Geneva, Switzerland

## Slide 6: Project Implementation
Projects to be administered in accordance with the guidelines of the Implementing Partner. Implementing Partners will apply their own approval procedures, procurement and financial management procedures, and project start-up support
Activities supported by CREWS include (but not limited to):
- analytical & advisory services
- investments and technical assistance activities
- capacity building
- operational support executed by the Implementing Partner
Changes to an existing project will be communicated to the CREWS secretariat by the Implementing Partner for approval by the Steering
(Changes include modifications of objectives, outcome targets, reallocation of inputs (more than a 10% change in a budget category), and/or extension of the completion date)
Steering Committee Meeting 12 September 2016 WMO, Geneva, Switzerland

## Slide 7: Partner Engagement
Steering Committee Meeting 12 September 2016 WMO, Geneva, Switzerland
National and regional institutions, Non-Governmental Organizations (NGOs), the private sector and CREWS contributing countries through NMHSs will need to be involved in CREWS, both in the design process for projects and their implementation.
UNISDR, WMO and World Bank have extensive networks of experts institutions and knowledge that CREWS will draw on. Other relevant networks are Global Framework for Climate Services (GFCS) and the International Network for Multi-Hazard Early Warning Systems (IN-MHEWS)
Stakeholders will engage in the different CREWS programming stages through the Implementing Partners and in accordance with the Implementing Partners policies.
Early warning systems requires close partnerships between many and varied organizations involved in the hazard monitoring, the dissemination of predictions, the issuance of warnings and the management of disasters

## Slide 8: Thank You