## Slide 1: Status update CREWS Pacific Regional Project:
Strengthening Hydro-Meteorological and Early Warning Services in the Pacific
CREWS Steering Committee
29 June 2017

## Slide 2: CREWS Pacific
Focus: Strengthening the Regional Specialized Meteorological Centre (RSMC Nadi) within the Fiji Meteorological Service (FMS) and the countries it serves:
  Fiji, Cook Islands, Kiribati, Niue, Tuvalu
  Some services to Samoa & Tonga
  Some services to non-WMO members Palau, Nauru, Republic of the Marshall Islands, Tokelau
Total funding: USD 3,500,000 (USD 1,000,000 co-funding from Canada (ECCC))
Implementation period: Jan 2017- Dec 2020

## Slide 3: Relation between the different projects
Caribbean SIDS
African SIDS
Pacific SIDS
Caribbean SIDS
African Countries
Pacific SIDS
PNG
Southeast Asia (SEA)
SEA
Canada CREWS SIDS-SEA (ECCC-funded)
CREWS Pacific SIDS
CREWS MDTF
Pacific/
Timor Leste
GCF
IKI, UNESCAP, etc.

## Slide 4: Preliminary budget distribution across the regions
Components/Regions | ECCC |  | CREWS |  | Total
 | % | USD | % | USD | USD
SEA | 53 | 3,891,336 | - | - | -
Pacific SIDS | 13 | 1,248,164 | 76 | 1,900,000 | 3,148,164
(African SIDS) | - | - | - | - | -
Caribbean SIDS | 6 | 440,529 | - | - | -
Project Management | 7 | 513,950 | 10 | 175,000 | -
Communications, M&E | 4 | 293,686 | 4 | 100,000 | 
Indirect costs (PSC) | 13 | 954,479 | 13 | 325,000 | -
Total | 100 | 7,342,144 | 100 | 2,500,000 | 9,842,144

## Slide 5: Progress to date
Revision of outcomes and outputs to ensure alignment and optimal use of funds between the ECCC-funded project and the CREWS-funded project
Revision and specification of activities and preliminary costing in cooperation with WMO Regional Office for Asia & the South-West Pacific and WMO technical departments
Recruitment for project management staff initiated
Creation of the Project Steering Committee with country representatives initiated ( leverage PMC meeting in August)
Institutional strengthening of FMS through Strategic Plan Development

## Slide 6: Aligning the outcomes of the two projects
CREWS-funded project:
  Governance:
  A) Institutional Strengthening of FMS, RSMC Nadi and NMHS in the PICTs
  Enhancement of capacities
  B) Capacity building and implementation support
  Upgrading facilities
  C) Modernization of forecasting facilities
  Improved service delivery:
  D) Improvement of meteorological and hydrological service delivery
  E) Community-based EWS in selected countries
ECCC-funded project:
Governance:
  Strengthened governance structures/ mechanisms for targeted Regional Centres and NMHSs are in place
Enhanced product development & accessibility:
  Enhanced regional and national facilities and capacities to produce impact-based forecasts and risk-informed warnings of extreme/high-impact hydro-meteorological events
Improved service delivery:
  Participating Regional Centres and NMHSs (better) deliver impact-based and risk-informed hydro-meteorological data, products and services to MHEWS stakeholders for decision support

## Slide 7: Outcomes and main “Service Lines” to address major hazards
SWFDP
FFGS, APFM
CIFDP
IDMP
Observations & Monitoring
Data Processing, Modelling, Forecasting, Predictions, Scenarios  Product Development, Infrastructure
Service Delivery, User Engagement, Applications
Severe Weather
Floods
Coastal Hazards
Drought
Coordination, Planning, Partnerships
Resource Mobilization
Outcome 1: Strengthened governance structures/ mechanisms for the Regional Centres/NMHSs targeted by the project are in place
Outcome 2: Enhanced product development and accessibility (incl. regional/national facilities and capacities)
Project Management
Outcome 3: Strengthened service delivery to MHEWS stakeholders for decision support
Service Delivery Strategy
DRR Roadmap, Framework/Mechanism for WMO Contributions to the GFCS
Capacity Development Strategy, Resource Mobilization/Partnership Strategy
FFGS, APFM
IDMP, GFCS
IDMP, GFCS (UIP)
FFGS, APFM
Risk (Hazard & Vulnerability) Assessments
SWFDP
SWFDP
CIFDP
CIFDP
Seamless GDPFS
WIS
WIGOS
GOS
HYCOS
GOOS
GCOS, GFCS (OBS)
RCCs
CSIS
Storms, incl. Tropical Cyclones

## Slide 8: Next Steps
Regional stocktaking of existing capacity/needs assessments and on-going project (desktop consultancy)
Project Steering Committee Meetings:
  For the CREWS Pacific and ECCC projects during the Pacific Meteorological Council (PMC-4) meeting in August in Honiara, Solomon Islands
  For SEA (ECCC project) in October in Hanoi, Vietnam
First workshops:
  In-country CAP Jump-Start Workshops in Pacific SIDS (July/August) (Outcome 3)
  Country-level strategic planning (Outcome 1)
SIDS event at COP23 in November in Bonn, Germany

## Slide 9: Annual work plan 2017/18
OUT-COMES | OUT-PUTS | Year 1 | Year 2 |  |  |  |  |  |  |  |  |  |  | 
 |  | 2017 |  |  |  |  |  |  |  |  |  | 2018 |  | 
 |  | Q1 | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | 
 |  | Jan-Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
1 | 1.1 |  |  |  |  | Stocktaking |  |  |  |  |  |  |  | Governance Workshops
 | 1.2 | Fiji Strategic Plan |  |  |  |  |  |  | Strategic plans (national level) |  |  |  |  | 
 | 1.3 |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 2.1 |  |  |  |  |  |  |  | NWP Vietnam |  |  |  |  | 
 | 2.2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2.3 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2.4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2.5 |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | 3.1 |  |  |  |  | CAP Workshops |  | Regional Workshops |  |  |  |  |  | 
 | 3.2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 3.3 |  |  |  |  |  |  | Fiji NCOF? |  |  |  |  |  | 
 | 3.4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 3.5 |  |  |  |  |  |  |  |  |  |  |  |  | 
0 (Project Mgmt) | 0.1 | Salaries |  |  |  |  |  |  |  |  |  |  |  | 
 | 0.2 | Travel |  |  |  |  |  |  |  |  |  |  |  | 
 | 0.3 |  |  |  |  |  | PSC Pacific |  | PSC SEA |  |  |  |  | 
 | 0.4 |  |  |  |  |  |  |  |  | COP |  |  |  | 
 | 0.5 |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 10
Thank you
Merci
Jochen Luther (jluther@wmo.int)  SEA, African & Caribbean SIDS
Lina Sjaavik (lsjaavik@wmo.int)  Pacific SIDS